## AGREEMENT 2017
WORK ORDER/ CONTRACT
Ref No- CO/2017-18/001 |  |  |  |  | DATED: 05/11/2017
1. SCOPE OF WORK :
Work includes, Development , hosting, testing and maintenance of Website as per required by the user( Connecting One Enterprises). As per annexure (Attached)
2. CONTRACT PERIOD:
AS per Mutually agreed and decided by both the Parties , that is
Within 90 days, Not exceeding 120 days.
3. COST / CHARGES: Total cost inclusive of GST is Rs. 3,90,000/- (Three Lac Ninety Thousand Only)
4. SERVICE TAX: As applicable as per present tax structure.
5. PAYMENT TERMS.
As per mutually decided by the team (Retinodes and Connecting One) . Breakup of payment terms as mentioned below.
1. At the time of initiation of Work |  |  |  |  | - 20% of total value.
2. Milestone-1 (Upfront) |  |  |  |  | -10%
3. Milestone-2 (Design) |  |  |  |  | -10%
4. Milestone- 3 (Programming and Development) |  |  |  |  | -15%
5. Milestone-4 (Delivery and Launch) |  |  |  |  | -15%
6. Full & Final payment after Completion certificate |  |  |  |  | -30%
6. WARRANTY / MAINTENANCE CHARGES:
For first year maintenance charges is not applicable and after that AMC would be made and cost for the same would be mutually decided.
7. DEDUCTION : As per Existing Rule of TDS.
8. ANNEXURE : Terms and Conditions attached
9. Additional Point to be noted:
1. Apart from android plate form, it will also work on (IOS)safari web browser.
2. Trouble shooting period will be decided mutually.
ANNEXURE
DEVELOPMENT MODULES
| Particulars | Description
| Modules | 1 | Social Networking
|  | 2 | Member ship management ( Multi Level Marketing concept based)
|  | 3 | Member Earning management
|  | 4 | Company Ad management
|  | 5 | Survey and Click Add Management
|  | 6 | Post Free AD
|  | 7 | Home Page Activities
| Controls | 1 | Registration/Login
|  | 2 | Admin Control & Login
|  | 3 | Create & Alter Profiles (Like Primary profiles, Contact profiles, social profiles,personal or professional profiles etc.)
|  | 4 | Create & Alter Members & Membership profiles
|  | 5 | Create & Alter Ad Services
|  | 6 | Image uploading
|  | 7 | Chat Server (Text & Video) Integration
|  | 8 | Email Integration
|  | 8 | Message Integration
| Admin Controls | 1 | Ability to Manage Accounts
|  | 2 | Manage Profile Details
|  | 3 | Manage Profile Settings, Change Password’s
|  | 4 | Ability to Manage (Add/Edit/Delete) Members
|  | 5 | Admin Management & Activities (Administrator)
|  | 6 | Create & Manage Home Page Activities
|  | 7 | Create & Manage Advertising related services
| Application | 1 | Primary Features of Social Networking Module
| Features | i. | Registration Page
|  |  | a) | Member or User Registration From
|  |  | b) | OTP generation or email
|  |  | c) | OTP Verification or Email Verify
|  |  | d) | Password Generation
|  |  | e) | Password Set on email
|  | ii. | Login Page
|  |  | a) | User Id/ Mobile No
|  |  | b) | Social Site login Integration like FB, etc
|  |  | c) | Password management
|  |  | d) | Forgot Password
|  |  | e) | Reset password and email
|  | iii. | Profile
|  |  | a) | Primary Profile Details
|  |  | b) | Contact Profile Details
|  |  | c) | Social Profile Details
|  |  | d) | Personal Profile Details
|  |  | e) | Family Profile Details
|  |  | f) | Professional Profile Details
|  |  | g) | Security Profile Details ( public / private )
|  |  | h) | Password Setup
|  |  | i) | Active / Deactivate Account
|  |  | j) | Upgrade Account
|  |  | k) | Earning Profile: Banking Details, Wallet, Transactions
|  | iv. | Social Activity
|  |  | a) | Friend Request
|  |  | b) | Post
|  |  | c) | Wall
|  |  | d) | Chat with other Users
|  |  | e) | Create Group
|  |  | f) | Image , Text , Video Sharing
|  |  | g) | AD management
|  |  | h) | Earning Survey
|  |  | i) | Click on Payable AD
|  |  | j) | Search non friend member by name, place
|  |  | k) | See non friend member profile
|  |  | l) | Show Profile Details
|  |  | m) | Edit Details, Timeline Activities viewer
|  |  | n) | Comments & Rating Viewer and post
|  |  | o) | Show all notification , comment , request , my new ad, survey
|  |  | p) | User status viewer
|  | 2 | Member ship management ( Multi Level Marketing concept based)
|  |  | 2.1 | Upgrade member Ship Plan
|  |  | 2.2 | View Down level
|  |  | 2.3 | Generate referral link to join member
|  |  | 2.4 | Member Group Activity Dashboard
|  |  | 2.5 | View No of levels Connected
|  |  | 2.6 | View income Line
|  |  | 2.7 | Credit Statement
|  |  | 2.8 | Request for point redeem
|  |  | 2.9 | Edit member ship profile
|  |  | 2.1 | Member Ship payment Methods management
|  |  | 2.11 | My transactions and receipts
|  | 3 | Member Earning management
|  |  | 3.1 | View Payable Ad Inbox
|  |  | 3.2 | View outbox of Done AD
|  |  | 3.3 | View Credit Statements
|  |  | 3.4 | View Free Ad, Profitable Ads, Survey, Transactions, Payments, Wallets and
Earning points
|  | 4 | Company Ad management
|  |  | 4.1 | Ad vendor Management
|  |  | 4.2 | Ad content Management like ad link , or company person create ad
|  |  | 4.3 | Ad Editor
|  |  | 4.4 | Ad costing and payment
|  |  | 4.5 | Ad vendor activities and payment setup
|  |  | 4.6 | Assign Ad to members
|  | 5 | Survey or Click Ad management
|  |  | 5.1 | Survey vendor Management
|  |  | 5.2 | Survey content Management like ad link , or company person create ad
|  |  | 5.3 | Survey Editor
|  |  | 5.4 | Survey costing and payment
|  |  | 5.5 | Survey vendor activities and payment setup
|  |  | 5.6 | Assign survey to members
|  | 6 | Free Ad Posting
|  |  | 6.1 | Create AD POST
|  |  | 6.2 | Upload POST
|  |  | 6.3 | POST management like Category , listing area
|  |  | 6.4 | Location Mapping with POST publication
|  |  | 6.5 | Member or vendor notification
|  | 7 | Home page Activities
|  |  | 7.1 | You tube Sharing
|  |  | 7.2 | Top members List with earning
|  |  | 7.3 | Top Ad or brand
|  |  | 7.4 | Latest News & Blog
|  |  | 7.5 | Share market updates
|  |  | 7.6 | Different category banners
|  |  | 7.7 | Text Animation
|  |  | 7.8 | User Testimonial
|  |  | 7.9 | Free social media updates based on integration
TIME FRAME FOR THE COMPLETION OF DESCRIBED REQUIREMENT IS AS FOLLOWS
| REQUIREMENT | MODULES COVERED |  |  |  | WORK LOADS
| DAY 01- DAY 120 | Website Application Development & Android App Development |  |  |  | 120 DAYS (Max)
| DOMAIN | Valid up to 12 Months from Date of Purchase |  |  |  | 860 INR ((Inclusive in cost))
| HOSTING | Valid up to 12 Months from date of purchase |  |  |  | 2082 INR(Inclusive in cost)
| ENTITIES | 1 Project Manager, 3 Web Developer, 1 Database Administrator, 1 Designer, 1 Android Developer, 1 Graphic Designer, 1 Tester |  |  |  | 09 DEVELOPERS
| CHARGES | Cost estimate on basis of Days & Entities (inclusive 18% GST) |  |  |  | 3,90,000 INR
| WORKING | WORK DESCRIPTION
DAYS
| 1 Day- 15 | Discovery and planning– This is one of the most crucial stages of the project as it is at this stage
| Days | that the foundation for the success of the project is determined. Areas covered at this stage may
include research; discovery sessions; writing of creative brief; writing of a technical briefs or more
detailed architecture, requirements and definitions document; site architecture plan; wireframes
and sitemap creation.
| 30-40 | Design -Based on the creative brief and information gathered in the discovery stage the project
| Days | will then move to the design stage. It is at this stage that design mock ups are created and
presented for feedback to establish a design that meets the goals of the new application.
| 40-50 | Programming & Development - Using the approved design, site architecture, technical brief and
| Days | sitemap the project then moves to the development stage. This is where the android application
comes to life and all the elements of the site come together to produce a high quality application.
| 10 – 15 | Beta Testing- Once the application has been developed it then goes to a beta testing stage. The
| Days | opportunity is given to the client to share the application with the necessary stakeholders for review and
feedback in a password-protected location.
Enhancements (ongoing) – Once an application has gone live, there is always
room for ongoing improvements and updates. Updations or Modifications may be chargeable.
1) Project Manager : Ashish Pawar, ashishpawar947@gmail.com
2) Web Developer: Bijendra Sahu, retinodes.bijendra@gmail.com
3) Database Administrator: Rohit Chaturvedi, retinodes.rohit@gmail.com
4) Designer: Pinku Kesharwani, retinodes.pinku@gmail.com
5) Android Developer: Amit Sharma, retinodes.amit@gmail.com
6) Graphic Designer: Vaishali Bhargav, retinodes.vaishali@gmail.com

## STATUS 2018
C1 PROJECT STATUS & NEW REQUIREMENTS
Sr No | AS IN AGREEMENT | STATUS AS ON OCT 2018 | REMAINING WORK FROM AGREEMENT | DEAD LINE | NEW WORK OUT OF AGREEMENT | DEAD LINE
1 | ANDROID APPLICATION | PARTIALLY DONE | Application not fully developed : Meed Testing & Improvements as said below in the Table |  | IOS APPLICATION
2 | IOS WEB BROWSER (Pinku) Scope | PARTIALLY DONE | WINDOWS BROWSER,IOS BROWSER SHALL HAVE SAME DESIGN & FEATURES | 2018-10-29 | APPLICATION LOGO : Mobile APP Logo design
| Scope | NOT COMPLETED | Center Window for Post should be squeezed down to the size required/fit to Photograph compatibility (So the post will look better same as FB) | 2018-10-29
1 | Modules : Social Networking
A | Login Page(Scope) Bijendra | NOT COMPLETED | Password View (Eye) should be added which is missing | 29-10-2018(Done) | Last Login Date (DD/MM/YY) & Time (12 HRS)
| Not in Scope | NOT COMPLETED | Language Selection : English (US),HINDI | Not in contract | Time spent on Connecting one/Total login time hrs:min:sec (Web or app or WAP)
Ristriction (When allowed time limit exceeds user should logout automatically with 5 mins warning)
User can extend time manualy (5 min,1hr,24 hr)
Emergency numbers (Direct dial)
B | Registration Page(Scope) Pinku | NOT COMPLETED | When on login page "REGISTRATION" should flash & when on Registration Page "LOGIN" should flash to bring attention of User to these pages | 2018-10-29 | Create Business Profile (Paid Version)
| (Bijendra)Scope | NOT COMPLETED | Refferal Code : Small message needs to be given "USE YOUR FRIEND REFFERAL CODE OR PROMO CODE YOU RECCEIVED ON SUCCESSFUL COMPLETION OF THE SURVEY" | 29-10-2018(Done) | Create Celebrity Profile (Paid Version)
| (Bijendra)Scope | PARTIALLY DONE | DROPDOWN FOR CITY NOT THERE | Already Altered
| (Bijendra)Scope | PARTIALLY DONE | EMAIL EXTENSION RESTRICTION NOT REQUIRED | Already Altered(Done)
| (Bijendra)Scope | NOT COMPLETED | AGE CALCULATION NOT GIVEN AFTER PUTTING DOB SINCE OUR RESTRICTION IS 18Yrs & ABOVE | 29-10-2018(Done)
| (Bijendra)Scope | NOT COMPLETED | Re Enter password for matching is missing | 29-10-2018(Done)
| (Pinku)Scope | NOT COMPLETED | Message on Registration page : By clicking SUBMIT, you agree to our Terms & Conditions, Data Policy and Cookies Policy. You may receive SMS or Email Notifications from us and can opt out any time. | 2018-10-30
| (Pinku)Scope | PARTIALLY DONE | FAQ : Language used in FAQ is incorrect & need revision | Please provide
| (Pinku)Scope | PARTIALLY DONE | ABOUT US : Correct Pictures needs to be updated | Please provide
| (Amit)Scope | PARTIALLY DONE | Google Play : Read More category discription is displayed 2 Times one after another. Delete what is repeated. | 2018-10-30
C | Profile(Bijendra) | NOT COMPLETED | Active / Deactivate Account | need to discuss
| (Bijendra)Scope | NOT COMPLETED | Report Profile (Fake,Nudity,Voilence,Hate Speech,Terrorist,Using Details of My Profile) | 29-10-2018(Done)
| (Bijendra+Amit)Scope | PARTIALLY DONE | Earning Profile (Only Level 0 is visible full network visibility is required) Banking Details (Where databse will store details) | Web - Already Working(Done) Android - Already Working
| (Bijendra)Scope | PARTIALLY DONE | Wall profile : It should display only post of user & not any other connection since this is a personal Wall | Web - Already Working(Done) Android - Already Working
D | Social Activity | NOT COMPLETED | Post : 1) Post Dropdown should appear before posting anything (Share to : Public,Friends,Group/Groups),After choosing group list of all his/her Groups should appear or if choosing Friends then list of all friends should appear to select & post | Ask to client | Create Network (Group)
| (Pinku)Scope | PARTIALLY DONE | Notifications appear but not able to close notification dropdown | 2018-10-29 | Create Event
| (Pinku)Scope | PARTIALLY DONE | Cannot select & see on notification that which post is liked or unliked or commented on | 2018-10-30 | Weather forecast
| (Bijendra)Scope | NOT COMPLETED | Checkin with location & option to post Image+Video | Working | Location Sharing
| (Bijendra)Scope | PARTIALLY DONE | What's on your mind should be changed to "CREATE YOUR POST HIMANSHU :)" | 29-10-2018(Done) | Health : (Sync App+Web+WAP) 1) Steps display 2) Cal Burnt 3) Drink Water reminder 4) Stand-up reminder
| Not in Scope(Pinku) | PARTIALLY DONE | What's on your mind HIMANSHU ! : It should add profile first name at the end of sentence with PEN icon (Moving left to right) | Ask to client | Integrate GIF
| Not in Scope(Pinku) | NOT COMPLETED | Picture rotation & cropping option not given on WEB & WAP | Ask to client | Integrate Stickers
| (Pinku)Scope | PARTIALLY DONE | Unlike icon (broken heart) not added on web/Wap browsers | Ask to client | Integrate 3D Emojis
| (Pinku)Scope | PARTIALLY DONE | Message : You can Upload Maximum 10 images of 3MB each & 1 Video of 15 MB This message should appear on APP/WEB/WAP all of them | Ask to client
| (Pinku+Bijendra)Scope | PARTIALLY DONE | When click on Publish : message Should appear "WE ARE UPLOADING YOUR POST QUICKLY" & when posted message should appear " SUCESSFULLY POSTED,KEEP GOING" | 2018-10-30
| (Pinku+Bijendra)Scope | NOT COMPLETED | Comment : Edit & delete comment option is missing in App/Web & WAP (User should be able to delete any comment on his personal post including himself/herself) | 2018-10-30
| (Bijendra)Scope | NOT COMPLETED | REPORT POST : 1) Give Feedback to owner of post 2) Hide Post 3) Report Post : New window should open with these options to select & report (Abuse,Sensored,Violence,False news,hate Speech,Spam,terrorism,fake profile). This will then be reviewed by C1 administration Panel for further action | 29-10-2018(Done)
| Not in Scope | NOT COMPLETED | Sharing : (Not avbl on WEB/WAP/APP) 1) Share with Friend 2) Share with group 3) Share on own Wall | Ask to client/Already Alter(Only in app)
| Not in Scope | PARTIALLY DONE | Payable AD/Survey : It should be optional from Admin Profile,It should only appear when Enabled by Admin | Ask to client
| Need to ask | NOT COMPLETED | Search non friend member by name, place : Cannot search by Place | Ask to client
| Need to ask | PARTIALLY DONE | See non friend member profile : On non friend user only what is posted by himself + What is posted in Public should be seen by other users | Ask to client
| Not in Scope | NOT COMPLETED | Timeline Activities viewer ????? | Ask to client
| Not in Scope | NOT COMPLETED | Chat with other Users : Messanger still not developed | Ask to client
2 | Modules : Membership management ( Multi Level Marketing concept based)
| Not in Scope | NOT COMPLETED | Upgrade member Ship Plan | not in contract | For premium members Batch should be allocated to profile which indicate member is premium
| Scope | NOT COMPLETED | View Down level | already working | Separate Batch for Separate membership should be allocated after choosing plan
| Not in Scope | NOT COMPLETED | Member Group Activity Dashboard |  | Separate Batch for business Profile
| Scope | NOT COMPLETED | View No of levels Connected | already working | Separate Batch for Celebrity Profile
| Not in Scope | NOT COMPLETED | View income Line |  | Send reffaral code direct to FB,Insta,Whatsapp,Gmail,Linkdin, Twitter
| Not in Scope | NOT COMPLETED | Edit member ship profile |  | Amin Profile : Create Own Survey & Post them on Whatsapp+FB to generate Refferal code after successful complition of Survey & direct user to "connectingone Home page" to use that refferal for new registration
3 | Member Earning management
| Not in Scope | NOT COMPLETED | View Payable Ad Inbox : Admin control to Enable & Disable Ad | Ask to client
| Not in Scope | NOT COMPLETED | View outbox of Done AD | Ask to client
| Not in Scope | NOT COMPLETED | View Credit Statements | Ask to client
| Not in Scope | NOT COMPLETED | View Free Ad, Profitable Ads, Survey, Transactions, Payments, Wallets | Ask to client
4 | Company Ad management
| Not in Scope | NOT COMPLETED | Ad vendor Management | Ask to client
| Not in Scope | NOT COMPLETED | Ad costing and payment | Ask to client
| Not in Scope | NOT COMPLETED | Ad vendor activities and payment setup | Ask to client
| Not in Scope | NOT COMPLETED | Assign Ad to members | Ask to client
5 | Survey or Click Ad management
| Not in Scope | NOT COMPLETED | Survey vendor Management | Ask to client
| Not in Scope | NOT COMPLETED | Survey content Management like ad link , or company person create ad | Ask to client
| Not in Scope | NOT COMPLETED | Survey Editor | Ask to client
| Not in Scope | NOT COMPLETED | Survey costing and payment | Ask to client
| Not in Scope | NOT COMPLETED | Survey vendor activities and payment setup | Ask to client
| Not in Scope | NOT COMPLETED | Assign survey to members | Ask to client
6 | Free Ad Posting (BUY & SELL)
| Scope(1,2,3,4(simple multiple),6,7) | PARTIALLY DONE | Create AD POST 1) Selling Cost of Product (Mendatory in INR) 2) Email ID (Optional) 3) Phone number (Optional) 4) Multiple picture posting with rotation & cropping (Not more then 8) 5) Chatting with buyer (Paid service) 6) City Dropdown 7) Add Location (Optional) | 2018-10-30
| Scope | PARTIALLY DONE | Upload POST 1) After Upload Edit/Delete option should be given 2) Validity of Post | 2018-10-30
| Not in Scope | NOT COMPLETED | POST management like Category , listing area 1) Current Status open/Closed (Mandatory) 2) Edit Post Validity 3) Others : Additional Box to write what user mean by Other | Ask to client
| Not in Scope | NOT COMPLETED | Location Mapping with POST publication | Ask to client
| Not in Scope | NOT COMPLETED | Member or vendor notification 1) When Post is approved or declined with reason 2) Someone Like the Post 3) Someone Comment on the post 4) Someone Report the Ad Post (Admin control) | Ask to client
7 | Home page Activities
| Not in Scope | NOT COMPLETED | You tube Sharing : User can Share Youtube links on his/her wall & apperence should be same as FB | Ask to client | Integration : Convert one format of File to Another Format : https://www.ilovepdf.com
| Not in Scope | PARTIALLY DONE | Top Ad or brand : Ad Window is already provided
| Not in Scope | NOT COMPLETED | Latest News & Blog : Breaking News should flash on Separate window provided on User Home page next to advertisement in white backgroung | Ask to client | Integration : Photo & Video editor
| Scope | NOT COMPLETED | Share market updates : Shares profile should run on single strip above write Post & should run right to left on white stripe | 2018-10-31 | Blogging 1) Blogger Area for Each Profile 2) Add members/Share Blog 3) Join Blog request from any user 4) Video post on Blog (Max : 1 min) 5) Share Blog link on Home Page (Own,friend,group) 6) Follow or Unfollow Blogger 7) Report Blog
| Not in Scope | NOT COMPLETED | Different category banners | Ask to client
| Not in Scope | NOT COMPLETED | Text Animation | Ask to client
| Not in Scope | NOT COMPLETED | User Testimonial | Ask to client
| Not in Scope | NOT COMPLETED | Free social media updates based on integration | Ask to client
END